## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2175-swen-261-13-b Checker Masters
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that no one else is using my name when I enter my name containing only alphanumeric characters or spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that I am on the Signin page when I enter a name that contains one or more characters th0at are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Signin form. |  | SJD; 2/28/18; takes non-alphanumerical characters; SJD; 2/28/18; Resolved |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form for me to try a different name. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | SJD; 2/28/18 |  | MTD; 4/4/18; N/A for the future as now you can only click on players if they are not in a game. | Pass | JK; 4/16/18
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given a valid, initial game board when I drag a red piece to a white space then the piece should not be droppable. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | SJD; 2/28/18 |  | MTD; 3/27/18 | Pass | AO; 4/5/18
Player Sign-out | Given that I am currently signed in when I see the Home page then I must see a means to sign out. |  | N/A |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that I am signed in when I click on the sign out button then I expect to be signed out and taken back to the Home page. |  | N/A |  | MTD; 3/27/18 | Pass | AO; 4/5/18
Matchmaking | Given that I am on the home page when I look at a player who is not in a game then I see some indicator showing that they are not in a game. |  | N/A |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that I am on the home page when I look at a player who is in a game then I see some indicator showing that they are in a game (so I can't challenge them). |  | N/A |  | MTD; 3/27/18 | Pass | AO; 4/5/18
Player Turns | Given that I am a Player in a game when I make a move then it would be the opposing Player's turn |  | N/A |  | MTD; 3/27/18 | Pass | AO; 4/5/18
Valid Moves | Given that I am in a game and it's my turn, when I make a valid move then the move should complete without any errors or warning messages. |  | N/A |  | MTD; 3/27/18 | Pass | AO; 4/5/18
| Given that I am in a game and it's my turn, when I make an invalid move, then the move should not complete and I should see an error saying I tried to make an invalid move. |  | N/A |  | MTD; 3/27/18; Moving a piece to a valid location, then moving it to any other location, causes a NullPointerException. MTD; 4/4/18; Resolved | Pass | AO; 4/5/18
Jumps | Given that I am a Player in a game and it is currently my turn in the game when there is an opponents piece I can capture then I am able to make a single jump move and take that piece off the board and advance my piece. |  | N/A |  | MTD; 4/4/18; When taking a jump move and undoing it, you can’t make the move anymore (the piece you jumped was removed from the turn’s board) MTD; 4/5/18; Resolved | Pass | AO; 4/5/18
| Given that I am a Player in a game and it is currently my turn in the game when there are 2 or more opponents pieces that I can capture then I am able to make a multiple jump move and move those pieces off the board and advance my piece |  | N/A |  | MTD; 4/4/18 | Pass | AO; 4/5/18
| Given that I am a Player in a game and it is currently my turn in the game when I have multiple jumps that I can take then I am able to choose which jump I can make |  | N/A |  | MTD; 4/4/18 | Pass | AO; 4/5/18
Game Over | Given that I am a Player in a game when I win/lose the game then I expect to redirected back to the Home Page |  | N/A |  | MTD; 4/4/18 | Pass | AO; 4/5/18; Winning doesn't work .Got rid of all white pieces and nothing happened; SJD; 4/7/18
| Given that I am a Player in a game when it is my turn and I am unable to make a move then I will lose the game and be redirected to the Home page |  | N/A |  | MTD; 4/4/18 | Pass | AO; 4/5/18; When there are no moves left the game is still active MTD; 4/7/18; Resolved
| Given that I am a Player in a game when all my pieces have been eliminated from the board then I will lose the game and be redirected to the Homepage |  | N/A |  | MTD; 4/4/18 | Pass | AO; 4/5/18; see above; SJD; 4/7/18
| Given that I am a Player in a game, when my opponent loses the game, then I will win the game and be redirected to the home page. |  | N/A |  | MTD; 4/4/18 | Pass | AO; 4/5/18; see above; SJD; 4/7/18
Forfeiting | Given that I am a Player when I am in a game then I expect to be able to forfeit the game. |  | N/A |  | MTD; 4/4/18 | Pass | AO; 4/5/18
| Given that I am a Player in a game when I quit the application then I expect to forfeit the game. |  | N/A |  | MTD; 4/4/18 | Pass | AO; 4/5/18
| Given that I am a Player when I forfeit a game then I expect to be redirected to the home page. |  | N/A |  | MTD; 4/4/18 | Pass | AO; 4/5/18
| Given that I am a Player in a game, when my opponent forfeits the game then I will win the game and be redirected to the home page. |  | N/A |  | MTD; 4/4/18; 500 error given MTD; 4/5/18; Resolved | Pass | AO; 4/5/18; If it is the Player's turn, they are not redirected to the home page until they submit their turn (change your acceptance criteria); SJD 4/7/18; It must operate that way to stay within the vision document
Forced Moves | Given that I am a Player in a game when it is my turn and a jump move is possible then I have to make the full jump move in order to advance the game |  | N/A |  | N/A | Pass | MTD; 4/17/18
| Given that I am a Player in a game when it is my turn and a multiple jump move is possible then I must complete the entirety of the multiple jump move |  | N/A |  | N/A | Pass | MTD; 4/17/18
| Given that I am in a game, when it is my turn and more than one jump moves are possible, then I am forced to choose one of them to fully jump through. |  | N/A |  | N/A | Pass | MTD; 4/17/18
King Creation | Given that I am a Player in a game when one of my pieces makes it to the row furthest from me then that piece will become a King piece. |  | N/A |  | N/A | Pass | MTD; 4/11/18
King Movement | Given that I am a Player in a game when I have a King piece then it is able to move both forward and backward diagonally. |  | N/A |  | N/A | Pass | MTD; 4/11/18
| Given that I am a player in a game when I have a King piece and a multi jump move is possible then that move can be any combination of forward and backward jumps. |  |  |  |  | Pass | MTD; 4/11/18
King Capturing | Given I have a King when I jump a piece then I expect it to be removed properly. |  | N/A |  | N/A | Pass | MTD; 4/11/18
Storing Replays | Given I am a Player when I complete a game then I expect my game to be stored as a replay for later viewing. |  | N/A |  | N/A | Pass | MTD; 4/11/18
Listing Replays | Given I am a Player when I am on the home page then I expect to see a list of my past games as replays. |  | N/A |  | N/A | Pass | SJD; 4/12/18
Viewing Replays | Given I am a Player with replays when I see the list of replays then I expect to see a way to view the replay. |  | N/A |  | N/A | Pass | SJD; 4/12/18
| Given I am a Player with replays when I click to view a reply then I expect to be taken to a replay view of the game. |  |  |  |  | Pass | SJD; 4/12/18
| Given that I am a Player with replays when I view a replay then I am able to view each move in the replay. |  |  |  |  | Pass | SJD; 4/12/18
Player Help | Given I am a player when I am in a game then I expect to have a link to request help. |  | N/A |  | N/A | Pass | SJD; 4/17/18
| Given I am a player when I click the request help link then I expect to be shown where I can make a move. |  |  |  |  | Pass | SJD;4/17/18
| Given I am a player when I make a move after requesting help then I expect the valid move spaces to no longer be indicated. |  |  |  |  | Pass | SJD;4/17/18